## Summary
Meridian Health Analytics — Cybersecurity Gap Assessment & Risk Register
Framework: NIST Cybersecurity Framework (CSF) 2.0 · cross-mapped to the HIPAA Security Rule and NIST SP 800-53
FICTIONAL organization — prepared as a portfolio GRC work sample. All data is illustrative.
Maturity by CSF Function (0 = none, 4 = optimized)
Function | Avg Current | Avg Target | Avg Gap | Posture
GOVERN | 0.8 | 2.8 | 2 | Initial
IDENTIFY | 1.3 | 3.3 | 2 | Initial
PROTECT | 1.8 | 3.4 | 1.6 | Developing
DETECT | 1 | 3 | 2 | Initial
RESPOND | 1.3 | 2.8 | 1.5 | Initial
RECOVER | 1 | 2.5 | 1.5 | Initial
OVERALL | 1.2 | 3 | 1.8 | Initial
Risk Register Summary
Inherent Rating | Count | Residual (after remediation) | Count
Critical | 4 | Critical | 0
High | 8 | High | 0
Medium | 2 | Medium | 11
Low | 0 | Low | 3
Total risks | 14 |  | 14
Executive takeaways
• Overall maturity sits at ~Initial. Governance and Incident Response are the weakest functions and the fastest to improve.
• Three issues drive most risk: standing privileged access (no PIM), unmonitored alerts (no SIEM), and no tested IR / DR.
• HIPAA-specific exposure: no periodic risk assessment, lapsed workforce training, untracked BAAs, and no breach-notification runbook (60-day clock).
• A 180-day, three-phase roadmap moves the program from Initial toward Defined; Phase 1 is low-cost and closes the highest-severity gaps first.

## CSF Gap Assessment
Function | ID | Category | Current (0-4) | Target (0-4) | Gap | Observation | HIPAA / 800-53 mapping | Priority
GOVERN | GV.OC | Organizational Context | 1 | 3 | 2 | Mission-to-risk linkage undocumented; PHI obligations (HIPAA) not mapped to business objectives. | HIPAA §164.316; 800-53 PM-1 | High
GOVERN | GV.RM | Risk Management Strategy | 1 | 3 | 2 | No defined risk appetite or tolerance; risk decisions made ad hoc without a register. | 800-53 PM-9; RA-1 | High
GOVERN | GV.RR | Roles, Responsibilities & Authorities | 1 | 3 | 2 | Single part-time security lead; no RACI; security accountability not assigned in writing. | HIPAA §164.308(a)(2); 800-53 PM-2 | High
GOVERN | GV.PO | Policy | 1 | 3 | 2 | Security policies are ad hoc, uncirculated, and not reviewed on a cadence. | HIPAA §164.316(a); 800-53 -1 controls | High
GOVERN | GV.OV | Oversight | 0 | 2 | 2 | No leadership/board oversight of the cybersecurity program or its outcomes. | 800-53 PM-1; CA-1 | Medium
GOVERN | GV.SC | Cybersecurity Supply Chain Risk Mgmt | 1 | 3 | 2 | Cloud, MSP, and subprocessors not formally assessed; BAAs not centrally tracked. | HIPAA §164.308(b); 800-53 SR-3 | High
IDENTIFY | ID.AM | Asset Management | 2 | 4 | 2 | Partial asset inventory; ePHI data stores not classified or formally mapped. | HIPAA §164.310(d); 800-53 CM-8 | High
IDENTIFY | ID.RA | Risk Assessment | 1 | 3 | 2 | No periodic security risk assessment — a HIPAA Security Rule requirement. | HIPAA §164.308(a)(1)(ii)(A); 800-53 RA-3 | High
IDENTIFY | ID.IM | Improvement | 1 | 3 | 2 | No lessons-learned loop; findings from incidents/audits are not tracked to closure. | 800-53 CA-5; PM-4 | Medium
PROTECT | PR.AA | Identity Mgmt, Authn & Access Control | 2 | 4 | 2 | Entra ID + MFA for most users, but standing privileged access, shared admin accounts, no PIM, and no access reviews. | HIPAA §164.312(a); 800-53 AC-2/AC-6/IA-2 | Critical
PROTECT | PR.AT | Awareness & Training | 1 | 3 | 2 | No recurring security-awareness or phishing training; HIPAA workforce training lapsed. | HIPAA §164.308(a)(5); 800-53 AT-2 | High
PROTECT | PR.DS | Data Security | 2 | 4 | 2 | Encryption at rest/in transit is on, but PHI is unclassified, there is no DLP, and backups are untested. | HIPAA §164.312(e); 800-53 SC-28/SC-8 | High
PROTECT | PR.PS | Platform Security | 2 | 3 | 1 | Patching handled by MSP inconsistently; no hardening baselines (e.g., CIS) enforced. | 800-53 CM-6/SI-2 | High
PROTECT | PR.IR | Technology Infrastructure Resilience | 2 | 3 | 1 | Cloud redundancy exists but failover has never been tested. | 800-53 CP-2/SC-6 | Medium
DETECT | DE.CM | Continuous Monitoring | 1 | 3 | 2 | Defender/M365 alerts are generated but not monitored; no SIEM or central log aggregation. | HIPAA §164.308(a)(1)(ii)(D); 800-53 SI-4/AU-6 | Critical
DETECT | DE.AE | Adverse Event Analysis | 1 | 3 | 2 | No defined process to analyze or correlate events; alerts triaged reactively, if at all. | 800-53 AU-6/IR-4 | High
RESPOND | RS.MA | Incident Management | 1 | 3 | 2 | No formal incident response plan or defined severities/escalation. | HIPAA §164.308(a)(6); 800-53 IR-1/IR-8 | Critical
RESPOND | RS.AN | Incident Analysis | 1 | 2 | 1 | No forensic capability; log retention insufficient to scope an incident. | 800-53 IR-4/AU-11 | High
RESPOND | RS.CO | Incident Response Reporting & Comms | 1 | 3 | 2 | No breach-notification runbook — exposes the HIPAA 60-day notification deadline. | HIPAA §164.400-414; 800-53 IR-6 | Critical
RESPOND | RS.MI | Incident Mitigation | 2 | 3 | 1 | Containment is possible (device isolation) but undocumented and unpracticed. | 800-53 IR-4 | Medium
RECOVER | RC.RP | Incident Recovery Plan Execution | 1 | 3 | 2 | No tested disaster-recovery or business-continuity plan; ransomware recovery unproven. | HIPAA §164.308(a)(7); 800-53 CP-10 | High
RECOVER | RC.CO | Incident Recovery Communication | 1 | 2 | 1 | No internal/external recovery communication plan. | 800-53 CP-2/IR-6 | Medium

## Risk Register
Risk ID | Risk / Threat Scenario | CSF | L (1-5) | I (1-5) | Inherent Score | Inherent Rating | Treatment | Control / Remediation (and portfolio evidence) | Owner | Res. L | Res. I | Residual Score | Residual Rating
R-01 | Standing privileged access and shared admin accounts enable privilege abuse or insider misuse | PR.AA | 4 | 5 | 20 | Critical | Mitigate | Implement PIM (eligible, time-boxed, MFA+approval) and remove standing Owner. Evidence: AZURE-IAM repo (RBAC+PIM). | Security Lead | 2 | 4 | 8 | Medium
R-02 | No access reviews leave orphaned / excessive access, incl. departed staff and vendors | PR.AA | 4 | 4 | 16 | Critical | Mitigate | Quarterly access reviews + JML offboarding automation. Evidence: access-review & JML lifecycle repos. | IT / HR | 2 | 3 | 6 | Medium
R-03 | Incomplete MFA coverage and legacy auth allow account takeover of ePHI accounts | PR.AA | 4 | 4 | 16 | Critical | Mitigate | Enforce MFA for all, block legacy auth via Conditional Access. | Security Lead | 2 | 4 | 8 | Medium
R-04 | No incident response plan; HIPAA 60-day breach-notification deadline missed | RS.MA/CO | 3 | 5 | 15 | High | Mitigate | Build IR plan + breach-notification runbook with defined severities and timelines. | Security Lead | 2 | 4 | 8 | Medium
R-05 | Security alerts unmonitored (no SIEM) → long attacker dwell time and missed breaches | DE.CM | 4 | 4 | 16 | Critical | Mitigate | Aggregate logs to a SIEM; triage alerts. Evidence: Home-SOC and AI SOC alert-triage repos. | Security Lead | 2 | 3 | 6 | Medium
R-06 | Vendors / subprocessors unassessed and BAAs untracked → third-party PHI exposure | GV.SC | 3 | 5 | 15 | High | Mitigate | Vendor risk program; centralize and track BAAs; tier subprocessors. | Security Lead | 2 | 4 | 8 | Medium
R-07 | PHI unclassified with no DLP → exfiltration or accidental oversharing | PR.DS | 3 | 4 | 12 | High | Mitigate | Classify ePHI; deploy DLP policies in M365/Purview. | IT | 2 | 3 | 6 | Medium
R-08 | OAuth illicit consent grant gives a malicious app standing access to mailboxes/data | PR.AA | 2 | 4 | 8 | Medium | Mitigate | Restrict user consent; admin-consent workflow; detect grants. Evidence: entra-oauth-consent-defense repo. | Security Lead | 1 | 3 | 3 | Low
R-09 | Untested backups and no DR plan → ransomware causes prolonged outage and data loss | RC.RP | 3 | 5 | 15 | High | Mitigate | Immutable backups; documented, tested DR/BCP with RTO/RPO. | IT / MSP | 2 | 4 | 8 | Medium
R-10 | No security-awareness or phishing training → successful social engineering | PR.AT | 4 | 3 | 12 | High | Mitigate | Recurring awareness training + simulated phishing; HIPAA workforce training. | Security Lead | 2 | 3 | 6 | Medium
R-11 | Inconsistent patching and no hardening baseline → exploitation of known CVEs | PR.PS | 3 | 4 | 12 | High | Mitigate | Patch SLAs; CIS hardening baselines; scanning. Evidence: Vuln-Mgmt & pyvulnscan repos. | IT / MSP | 2 | 3 | 6 | Medium
R-12 | No periodic risk assessment (HIPAA §164.308 requires one) → unknown, unmanaged exposure | ID.RA | 4 | 3 | 12 | High | Mitigate | Stand up an annual risk-assessment program feeding this register. | Security Lead | 2 | 2 | 4 | Low
R-13 | Cloud misconfiguration (public storage, open management ports) exposes ePHI | PR.PS | 3 | 5 | 15 | High | Mitigate | Continuous cloud posture mgmt vs CIS; remediate drift. Evidence: azure-cloud-security repo. | Security Lead | 2 | 4 | 8 | Medium
R-14 | Insufficient log retention / forensics → cannot investigate or scope a breach | RS.AN | 3 | 3 | 9 | Medium | Accept→Mitigate | Define retention; centralize audit logs for forensics. | Security Lead | 2 | 2 | 4 | Low

## Remediation Roadmap
Phase | Action | Addresses (Risk / CSF) | Effort | Cost | Owner
Phase 1 — 0-30 days | Build IR plan + HIPAA breach-notification runbook | R-04 / RS.MA,RS.CO | Low | $ | Security Lead
Phase 1 — 0-30 days | Enforce MFA for all users; block legacy auth (Conditional Access) | R-03 / PR.AA | Low | $ | Security Lead
Phase 1 — 0-30 days | Inventory and centralize all BAAs; list subprocessors | R-06 / GV.SC | Low | $ | Security Lead
Phase 1 — 0-30 days | Turn on and begin monitoring Defender/M365 alerts | R-05 / DE.CM | Low | $ | Security Lead
Phase 2 — 30-90 days | Deploy PIM; quarterly access reviews; remove standing Owner | R-01,R-02 / PR.AA | Medium | $$ | Security Lead
Phase 2 — 30-90 days | Conduct first formal HIPAA risk assessment feeding this register | R-12 / ID.RA | Medium | $ | Security Lead
Phase 2 — 30-90 days | Stand up vendor risk program and tiering | R-06 / GV.SC | Medium | $ | Security Lead
Phase 2 — 30-90 days | Recurring security-awareness + simulated phishing training | R-10 / PR.AT | Low | $ | Security Lead
Phase 2 — 30-90 days | Implement immutable backups and run a DR test | R-09 / RC.RP | Medium | $$ | IT / MSP
Phase 3 — 90-180 days | Deploy SIEM / central log aggregation + triage workflow | R-05,R-14 / DE.CM,RS.AN | High | $$$ | Security Lead
Phase 3 — 90-180 days | Classify ePHI and deploy DLP (M365 Purview) | R-07 / PR.DS | Medium | $$ | IT
Phase 3 — 90-180 days | Enforce CIS hardening baselines + patch SLAs + cloud posture mgmt | R-11,R-13 / PR.PS | Medium | $$ | IT / MSP
Phase 3 — 90-180 days | Establish policy framework and leadership oversight cadence | GV.PO,GV.OV | Low | $ | Leadership